# UN/SCEGHS/7/INF.9

# COMMITTEE OF EXPERTS ON THE TRANSPORT OF

# DANGEROUS GOODS AND ON THE GLOBALLY

# HARMONIZED SYSTEM OF CLASSIFICATION

# AND LABELLING OF CHEMICALS

Sub-Committee of Experts on the Globally

Harmonized System of  Classification

and Labelling of Chemicals

(Seventh session, 14-16 July 2004,

agenda item 6)

COORDINATION AND WORK PROGRAMME

Progress in the Programme of Work for the biennium 2003-2004

As of June 2004

Note by the secretariat

The table on next page reflects the progress achieved regarding the programme of work of the Sub-committee for the current biennium and shows the situation of the various programme elements, together with their expected date of completion. This table aims at facilitating preliminary discussions about the elaboration of the workplan for the next biennium (2005-2006), discussions which will be launched during the seventh session..

| Programme of work 2003-2004 of the Sub-Committee of Expert on the Globally Harmonized System of Classification and Labelling of Chemicals |
| --- |
| Situation before the 7th Session of the SCEGHS |
| Programme elements | Responsible body | Submitted to the SCE GHS | Planned final date | Expected final date |
| Physical hazards |  |  |  |  |
| Health Hazards |  |  |  |  |
| Revision Chapter 3.1 | TF HCL OECD | to 7th SCE/INF doc | December 2004 | December 2004 |
| Toxic Gas Mixtures (TGM) | SCE GHS | to 7th SCE/INF doc | new element | no timeframe |
| Revision Chapter 3.8/Narc.effects | TF HCL OECD | to 7th SCE/official doc | December 2004 | December 2004 |
| Water-Activated Toxicity (WAT) | TF HCL OECD&SCE GHS | to 7th SCE/INF doc | December 2004 | December 2004 |
| Aspiration Hazards | TF HCL OECD | to 7th SCE/official doc | December 2004 | December 2004 |
| Sensitization/induction/ellicitation | TF HCL OECD | (c) | December 2004 | pursued on next biennium |
| Reproduction/chap 3.7 revision (a) | TF HCL OECD | to 7th SCE/official doc | December 2004 | December 2004 |
| Carcinogenicity (guidance) | TF HCL OECD | (c) | December 2004 | pursued on next biennium |
| Transformation/dissolution protocols for metals | TF HCL OECD | (c) | December 2004 | pursued on next biennium |
| Carcinogenicity/potency | TF HCL OECD | (c) | December 2006 ? | pursued on next biennium |
| Reproductive toxicity/potency | TF HCL OECD | (c) | December 2006 ? | pursued on next biennium? |
| senzitization strong/weak | TF HCL OECD | (c) | December 2006 ? | pursued on next biennium |
| Environment Hazards |  |  |  |  |
| Chronic aquatic toxicity hazards | TF HCL OECD | (c) | December 2006 ? | pursued on next biennium |
| Terrestrial Hazards | TF HCL OECD | 7th SCE/issue paper/INFdoc | - | pursued next biennium?(b) |
| Ozone depleting Substances | SCE GHS | to 7th SCE/INF doc | new element | no timeframe |
| Communication elements |  |  |  |  |
| Implementation Guidance |  |  |  |  |
| Labelling | SCE GHS | to 7th SCE/official doc+INF | December 2004 | December 2004 |
| Safety Data Sheets | SCE GHS | to 7th SCE/official doc | December 2004 | December 2004 |
| Precautionary Statements | SCE GHS | to 7th SCE/official doc+INF | December 2004 | December 2004 |
| International cooperation |  |  |  |  |
| Basel Convention | SCE GHS |  | new element | no timeframe |
| Cells with background highlighted in bright blue indicate programme elements to be pursued on next biennium 2005-2006 |
| Notes: |  |  |  |  |
| (a) Terminology only |  |  |  |  |
| (b) Decision to be taken by the SCE on the basis of the issue paper (7th session) |  |  |
| (c) OECD secrt. to report on the progress at the 7th SCE session |  |  |

# Text boxes

UN/SCEGHS/7/INF.9

page 2